RH-LeadGen
Sept 14, 8am, Zoom

Type of meeting
Activity Planning/Committments

Attendees
LD, RH, LR

Action Items
Item	Topic	Responsible	Time for Completion	Status
36	Feb Meet Dave Intro RFP TFSA	LR	2018-10-07	*
35	Article RSP TFSA Article	LD	2018-10-07	*
34	View Article Pic Linked	LR	2018-10-05	*
33	CADILLAcwealth.consulting
32	Blog Articles Pensions + Mortgage [Pubic + Private] posts on blogs + Li + Fb	LR + LD	2018-09-18	Pending
31	https://vidmsg.us/share/5b980d02ac820
30	articles.dwn.link Article Depository			Temp
29	https://pensionparadigm.dwn.link/			Vid Link
28	Email Addresses			Consistency
27	Meet up Slides – Overvoice into Video	LR RH LD		Pending
26	Article – LinkedIn – Major Banking	LR LD	2:00 Friday	Done
25	Blog Links – Video Links in	LR LD	2:00 Friday	Pending
23	Error Video Link Showing Suspended	LR	By Sept 10	Done
22	Agreement	LR	By Sept. 10	Pending*
21	Videos – Podcast – Videos – Joinme / 3 pensionvideo, wealth creation, tax management – post - Review	LR	Pending Audio Look because of Background. Oct.	Pending
20	Additional Blog Articles – current news	LD	DSC deferred Sales Charge Update Oct.7	Pending
12	Invite Next Meeting 8:30 am Oct 12	LR		Pending
11	Site – JoinMe – Add Article for Each Category -Psv-TSaav-CS?-ISaaav-MS	LD	Prority	*Pending Corp - Done
10	Site – JoinMe – Add Category – Tax Strategy – [2 articles ]	LR	Sept.7	Done
9	Blogspot – Link to Ralph.joinme	LR	Sept.7	Done
8	Blogspot – Add Author Bio – Link Ralph.joinme?	LD + LR	S	Done
7	Site FP – Access Godaddy	LD	Today	Done
6	Site Feedompro – Review	LR	2018-10-10	pending
4	LI Content Piece – Mortgage Insur	LD	Sept 13	Done
3	LI invites – 20	LR	Sept. 13	Done
2	LI Filter - Public Sector	LR	Sept. 13	Done
1	LinkedIn [LI] Followup	LD	Daily	Done

Additional information:
Please read

Notes